## Studymaterial -CS
No | Topic | Time | Objective | Expertise | Links/Material
1 | Good Understanding of Git | 0.5 Day | Start with Fundamental to advance java | Beginner | Youtube: 1. Git and GitHub for Beginners https://www.youtube.com/watch?v=Ak4Kvn682WY&list=PLS1QulWo1RIanDAyZJveQqKYH-iHA7tmZ 2. Git Tutorials (new) https://www.javatpoint.com/git-pull https://www.w3schools.com/git/git_intro.asp?remote=github
2 | Core Java + Design Patter + Solid OOPS practical knowledge (Java/C#) | 4 Weeks | Candidates need to do understand java concepts in detail | Intermediate | YouTube: 1. Java Tutorial For Beginners: https://www.youtube.com/playlist?list=PLS1QulWo1RIbfTjQvTdj8Y6yyq4R7g-Al Udemy: Java Programming for Complete Beginners https://www.udemy.com/course/java-the-complete-java-developer-course/?utm_source=adwords&utm_medium=udemyads&utm_campaign=Webindex_Catchall_la.EN_cc.UK_Experiment&utm_term=_._ag_148486679493_._ad_532713168385_._kw__._de_c_._dm__._pl__._ti_dsa-449490803887_._li_9045045_._pd__._&matchtype=&gclid=Cj0KCQjw756lBhDMARIsAEI0AgmyffwPldaVBmIjNiFBPJWppiItdxd40JvtvkBIB3fxbJ60pnokR4waAm2oEALw_wcB WorkShop/Practical can be performed online as well: https://www.w3schools.com/ https://www.javatpoint.com/ https://www.tutorialspoint.com/ https://www.hackerrank.com/ New https://www.softwaretestingmaterial.com/java-tutorial/
4 | Practice of a project and common Algorithm Questions | 1 Week |  | Beginner | https://github.com/learning-zone/java-basics https://github.com/learning-zone/java-basics/tree/master/java-programs New https://beknazarsuranchiyev.medium.com/top-17-java-coding-interview-questions-for-sdet-a978754eb078 New https://www.geeksforgeeks.org/output-of-java-program-set-2/
5 | Basic understanding of OS/Unix and SQL | 1 Day |  | Beginner | YouTube: 1. MySQL Tutorial for Beginners: https://www.youtube.com/playlist?list=PLS1QulWo1RIY4auvfxAHS9m_fZJ2wxSse https://www.softwaretestingmaterial.com/sql-joins-cheat-sheet/
6 | Excellent knowledge of Agile( and Jira wflow) | 0.5 Day | Backlog, sprint, Ticket, retro, refinement, and planning etc. | Beginner | YouTube: 1. JIRA CRASH COURSE for Beginners: https://www.youtube.com/watch?v=iryX1Oa1cMQ https://www.softwaretestingmaterial.com/jira-interview-questions/ 2. Agile: https://www.youtube.com/watch?v=WjwEh15M5Rw https://www.softwaretestingmaterial.com/category/agile/ https://www.softwaretestingmaterial.com/agile-testing-interview-questions/
7 | Practical Understanding of Junit and TDD/BDD | 3 Days | SQL queries, Join, transactions etc. , other tech: ORM, JDBC, ETL basics | Beginner | YouTube: 1. Cucumber (BDD) with Java/junit https://www.youtube.com/playlist?list=PLFGoYjJG_fqpObjigKg4bunu6_Ki7Ppn-
8 | Framework development - UI | 1 Week | Maven,Java,Selenium | Intermediate | YouTube: 1. Selenium Cucumber Java BDD Framework https://www.youtube.com/playlist?list=PLhW3qG5bs-L_mFHirOLEYJ7X2rIXu8SR2 https://www.softwaretestingmaterial.com/explain-test-automation-framework/
9 | Framework development - API | 3 Days | Junit, Mocking and TDD | Beginner | YouTube: 1. Rest API tutorials with framework creation: https://www.youtube.com/playlist?list=PL8VbCbavWfeE5aEeEpoXp2xiHi5K_7BMT
10 | Good experience on Jenkins/GITLab | 1 day | UI Framework Approach | Beginner | YouTube: 1. Jenkins Tutorial For Beginners : https://www.youtube.com/watch?v=yz3tyeA3Fe0&list=PLS1QulWo1RIbY8xXPqz6ad_sNHkIP3IXI https://www.softwaretestingmaterial.com/category/jenkins/
11 | What Practical issues comes in Automation and resolutions | 1 Day | API Framework Approach |  | https://www.lambdatest.com/blog/challenges-in-automation-testing/
12 | Mock Interview Question/Answers and CV Prep | 1 day | How to build CI and CD |  | YouTube: 1. Java Tutorial For Beginners: https://www.youtube.com/playlist?list=PLS1QulWo1RIbfTjQvTdj8Y6yyq4R7g-Al Udemy: Java Programming for Complete Beginners (Java Programming Course for Beginners to Java Object Oriented Programming. BONUS: Build REST API with Spring Boot.) WorkShop/Practical can be performed online as well: https://www.w3schools.com/ https://www.javatpoint.com/ https://www.tutorialspoint.com/ https://www.hackerrank.com/ New https://www.softwaretestingmaterial.com/java-tutorial/ https://www.javatpoint.com/scjp-quiz

## Ajay Tayde
S.No | Topic | Working Days |  | Start Date | Completion Date | Self Rating(5) | Material | Git repo URL |  | Status
|  | Estimated Days | Actual Days | [5 empty] | 2023-05-22 | 2023-05-26 | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-06-01 | 2023-06-02 | 2023-06-05 | 2023-06-06 | 2023-06-07 | 2023-06-08 | 2023-06-09
1 | Good Understanding of Git | 0.5 | 0.5 |  |  | 4 | Workshop |  | 2023-05-26: Completed
2 | Solid OOPS practical knowledge (Java/C#) | 20 | 12 | 2023-05-26 | 2023-06-09 | 4 | Video and Practice | https://github.com/atyeti-sdet-training/mahendra-chaudhari.git |  | 1.String,2.Array | 1.class, 2.Object , 3.Constructor, 4.Inharitance | 1.Polymorphism ,2.Encapsulation | 1.Abstraction, 2.Static Block, 3.ThisKeyword,4.SuperKeyword | 1.ArrayList,2.LinkedList | 1.LinkedList 2.practicing methods | 1.TreeSet 2.LinkedHashset 3.HashSet 4.Practicing Methods | 1.Map 2.HashMap 3.Practicing Methods | 1.Stream API 2.Intermediate Operations 3.Terminal Operations | 1.Exception Handling A.Checked B.Unchecked C.Throws D.Throw | *Design Pattern -Practicing related examples
4 | Practice of a project and common Algorithm Questions | 5 | 3 | 2023-06-12 | 2023-06-14 | 4 | Workshop |  | 2023-05-29: Practicing common examples of String and integers and arrays
5 | Basic understanding of OS/Unix and SQL | 1 | 1 | 2023-06-15 | 2023-06-15 | SQL-4, Unix-0 | Online websites |  | 2023-05-22: SQL Completed; 2023-05-26: Unix InProgress
6 | Excellent knowledge of Agile( and Jira wflow) | 0.5 | 1 | 2023-06-16 | 2023-06-16 | Jira-0, Agile-0 | A group session |  | 2023-05-22: Watching Videos
7 | Practical Understanding of Junit and TDD/BDD | 3 | 3 | 2023-06-22 | 2023-06-24 | 1 | Video and material
8 | Framework development - UI | 7 | 5 |  |  | 3 | Video and Practice
9 | Framework development - API | 3 | 3 |  |  | 2 | Video and Practice
10 | Good experience on Jenkins | 2 | 2 |  |  | 0 | Workshop
11 | What Practical issues comes in Automation and resolutions | 1 | 1 |  |  | 0 | Workshop
12 | Mock Interview Question answers and CV Prep | 1 | 1 |  |  | - | Workshop
| Total No. of Days | 43.5 | 32
S.No | Topic | Working Days |  | Start Date | Completion Date | Self Rating(5) | Material | Git repo URL | 2023-05-26: Status
|  | Estimated Days | Actual Days | [5 empty] | 2023-10-03 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 | 2023-10-14
1 | Good Understanding of Git | 0.5 | 0.5 |  |  |  | Workshop |  | 2023-10-04: Completed
2 | Solid OOPS practical knowledge (Java/C#) | 4 Weeks |  |  |  |  | Video and Practice |  |  | 1.String,2.Array | 1.class, 2.Object , 3.Constructor, 4.Inharitance | 1.Polymorphism ,2.Encapsulation | 1.Abstraction, 2.Static Block, 3.ThisKeyword,4.SuperKeyword | 1.ArrayList,2.LinkedList | 1.LinkedList 2.practicing methods | 1.TreeSet 2.LinkedHashset 3.HashSet 4.Practicing Methods | 1.Map 2.HashMap 3.Practicing Methods | 1.Stream API 2.Intermediate Operations 3.Terminal Operations | 1.Exception Handling A.Checked B.Unchecked C.Throws D.Throw | *Design Pattern -Practicing related examples
4 | Practice of a project and common Algorithm Questions | 1 Week |  |  |  |  | Workshop |  | 2023-10-05: Practicing common examples of String and integers and arrays
5 | Basic understanding of OS/Unix and SQL | 1 Day |  |  |  | SQL-, Unix- | Online websites |  | 2023-10-03: SQL Completed; 2023-10-04: Unix InProgress
6 | Excellent knowledge of Agile( and Jira wflow) | 0.5 Day |  |  |  | Jira-, Agile- | A group session |  | 2023-10-03: Watching Videos
7 | Practical Understanding of Junit and TDD/BDD | 3 Days |  |  |  |  | Video and material
8 | Framework development - UI | 1 Week |  |  |  |  | Video and Practice
9 | Framework development - API | 3 Days |  |  |  |  | Video and Practice
10 | Good experience on Jenkins | 1 day |  |  |  |  | Workshop
11 | What Practical issues comes in Automation and resolutions | 1 Day |  |  |  |  | Workshop
12 | Mock Interview Question answers and CV Prep | 1 day |  |  |  |  | Workshop
| Total No. of Days | 0 | 0
Formulas:
Completion Date = [Start Date]+D4+2